## Financial Management
Cost Estimation
Task Item |  | Participating Roles | Number of Participants | Estimated Total Person-Hours | Total Cost (£)
Team Formation & Kick-off | Team member familiarization & ice-breaking meeting | All Members | 6 | 4 | 1000 | Item | Time (h) | Hourly Rate (£/h) | Amount (£)
| Establish team communication norms & tools | All Members | 6 | 2 | 500 | Budget - papering | 51 | 250 | 12750
Project Management Framework Setup | Define team management structure & role responsibilities | All Members | 6 | 4 | 1000 | Budget - simulation | 765 | 250 | 191250
| Develop internal team meeting protocols | Project Manager | 1 | 2 | 500 | Total Budget | 816 | 250 | 204000
| Create project management templates (initial TAR) | Project Manager | 1 | 4 | 1000 | Spend - semester1-week2&3 | 120 | 250 | 30000
Project Planning & Definition | Analyze project specification & requirements | All Members | 6 | 6 | 1500 | Spend - semester1-week4&5 | 120 | 250 | 30000
| Determine tech stack & software environment | All Members | 6 | 4 | 1000 | Spend - semester1-week6&7 | 240 | 250 | 60000
| Create Work Breakdown Structure (WBS) | All Members | 6 | 6 | 1500 | Spend - semester1-week8&9 | 240 | 250 | 60000
| Develop preliminary Gantt chart / project timeline | Project Manager | 1 | 6 | 1500 | Total Spend | 720 | 250 | 180000
Cost Estimation & Kick-off Preparation | Detailed person-hour & cost estimation | Project Manager | 1 | 2 | 500 | Remaining Budget | 96 | 250 | 24000
| Prepare materials for initial supervisor meeting (plan, cost) | All Members | 6 | 4 | 1000 | Budget Utilization | 88.24%
| Conduct initial supervisor meeting (1 hour) | All Members | 6 | 1 | 250
| Post-meeting plan revision & confirmation | Project Manager | 1 | 2 | 500
Technical Preparation | Configure shared development environment (Git, MATLAB, etc.) | All Members | 6 | 4 | 1000
Subtotal |  |  |  | 51 | 12750
Weeks 1-2: Basic Modeling | NAO6 Robot Dynamics/Kinematics Modeling | Robot Model Developer | 1 | 30 | 7500
| Football Physics Model & Motion Simulation | Environment & Ball Developer | 1 | 25 | 6250
| Simulation Architecture Design & Environment Setup | Simulation Lead | 1 | 25 | 6250
| Project progress tracking & coordination | Project Manager | 1 | 10 | 2500
Weeks 3-4: Core Algorithm Development | Basic robot locomotion, turning motion control | Motion Control Developer | 2 | 60 | 15000
| Kicking, balancing motion control algorithms | Motion Control Developer | 2 | 50 | 12500
| Path planning & obstacle avoidance algorithms | Motion Control Developer | 2 | 40 | 10000
| Striker behavior state machine design | Behavior Algorithm Developer | 2 | 50 | 12500
| Defender behavior state machine design | Behavior Algorithm Developer | 2 | 50 | 12500
| Goalkeeper behavior logic | Behavior Algorithm Developer | 2 | 30 | 7500
Weeks 5-6: System Integration | Robot model & motion control integration | Simulation Lead | 1 | 20 | 5000
| Behavior algorithm & motion control interface integration | All Developers | 5 | 75 | 18750
| Competition field visualization development completion | Environment & Ball Developer | 1 | 30 | 7500
Weeks 7-8: Testing & Optimization | Single robot functional testing & debugging | All Developers | 5 | 100 | 25000
| Multi-agent team collaboration testing | All Developers | 5 | 80 | 20000
| Strategy optimization & performance tuning | Behavior Algorithm Developer | 2 | 40 | 10000
| Simulation verification & test report writing | Simulation Lead | 1 | 20 | 5000
| Phase progress management & reporting | Project Manager | 1 | 30 | 7500
Subtotal |  |  |  | 765 | 191250
Weeks 1-2: Hardware Prep & Code Migration | Hardware test plan development & NAO6 access arrangement | Hardware Test Lead | 1 | 20 | 5000
| Simulation code adaptation & migration to NAO6 platform | Code Migration Engineer | 1 | 40 | 10000
| Basic communication framework & API debugging | Code Migration Engineer | 1 | 20 | 5000
| Hardware resource coordination & safety management | Project Manager | 1 | 15 | 3750
Weeks 3-5: Motion System Calibration | Single robot basic walking calibration | Motion Calibration Engineer | 2 | 60 | 15000
| Kicking motion parameter calibration & optimization | Motion Calibration Engineer | 2 | 50 | 12500
| Multi-robot motion coordination testing | Motion Calibration Engineer | 2 | 40 | 10000
| Sensor data validation & processing | Motion Calibration Engineer | 2 | 30 | 7500
Weeks 4-6: Behavior Logic Testing | Striker behavior field testing & adjustment | Behavior Test Engineer | 2 | 60 | 15000
| Defender behavior field testing & adjustment | Behavior Test Engineer | 2 | 50 | 12500
| Goalkeeper behavior field testing & adjustment | Behavior Test Engineer | 2 | 40 | 10000
| Team collaboration strategy field validation | Behavior Test Engineer | 2 | 50 | 12500
Weeks 5-7: System Integration Testing | Full system integration & end-to-end testing | System Integration Engineer | 1 | 60 | 15000
| Full match scenario rehearsal | All Hardware Members | 5 | 100 | 25000
| Performance bottleneck diagnosis & optimization | System Integration Engineer | 1 | 40 | 10000
Week 8: Review Preparation | Hardware test report & performance analysis | Hardware Test Lead | 1 | 20 | 5000
| Design review material preparation | All Members | 6 | 48 | 12000
| Final phase management & reporting | Project Manager | 1 | 25 | 6250
Subtotal |  |  |  | 768 | 192000
Design Review Presentation (Feb 2026) | Design Review PPT creation | All Members | 6 | 36 | 9000
| Simulation demo preparation & testing | Simulation Lead | 1 | 15 | 3750
| Presentation rehearsal & content refinement | All Members | 6 | 18 | 4500
Final Demo Preparation (Mar 2026) | Final presentation PPT creation | All Members | 6 | 48 | 12000
| Hardware/software demo integration | All Members | 6 | 60 | 15000
| Final presentation rehearsal | All Members | 6 | 24 | 6000
Final Report Writing (Apr 2026) | Finalize report structure & outline | All Members | 6 | 18 | 4500
| Technical content writing & integration | All Members | 6 | 90 | 22500
| Cost analysis & project management section | Project Manager | 1 | 20 | 5000
| Report proofreading, formatting & finalization | All Members | 6 | 36 | 9000
| TAR form consolidation & submission | Project Manager | 1 | 10 | 2500
| Peer review collection & submission | All Members | 6 | 12 | 3000
| Final materials packaging & submission | Project Manager | 1 | 8 | 2000
Subtotal |  |  |  | 395 | 98750
Expert Help Budget Details | Senior Technical Consultation | All Members | 6 | 1 | 1250
| Senior Technical Consultation | All Members | 6 | 1 | 1250
Subtotal |  |  |  |  | 2500
Contingency Reserve | Task delay buffer |  |  | 30 | 7500
| Technical challenge response |  |  | 30 | 7500
| Hardware accidental damage |  |  | 30 | 7500
Subtotal |  |  |  |  | 22500
GRAND TOTAL |  |  |  |  | 519750

## Skills Management (hidden)
1. Proficiency Level: Use a consistent scoring system. * 1 - Novice: Aware of basic concepts, requires close supervision and guidance. * 2 - Beginner: Can perform tasks with assistance and guidance. * 3 - Competent: Can perform tasks independently and reliably; the primary resource for this skill. * 4 - Proficient: Can guide others, solve complex problems, and improve processes. * 5 - Expert: Recognized authority, can set standards, drive innovation, and train others. 2. Interest Level: Crucial for employee engagement and development planning. * H (High): Very interested, wants to develop and use this skill more. * M (Medium): Moderately interested, willing to work with it. * L (Low): Not interested, prefers to avoid tasks requiring this skill.
Team Member | Core Competency Area | Specific Skill / Tool | Proficiency Level (1-5) | Interest Level (H/M/L) | Notes
Yunhao Huang | Technical Skills | Unity 3D | 4 | H
|  | Matlab | 3 | M
|  | SoildWorks | 2 | L
|  | Circuit design/welding | 3 | M
| Programming Skills | C | 3 | H
|  | C# | 4 | M
|  | Python | 3 | M
| Project Management | Agile | 5 | H
Xuanwei Ge | Technical Skills | Azure | 2 | M
|  | Simul8/AutoCAD | 2 | M
|  | Multisim/UltiBoard/Soilding | 4 | M | FYP
|  | Adobe Audition | 4 | M | Audio Processing
| Programming Skills | EDA Playground | 4 | M
| Project Management | MS Project | 4 | M
Lingyu Guo | Technical Skills | Simulink | 4 | M
|  | Matlab | 3 | M
|  | Multisim | 2 | M
| Programming Skills | Python | 4 | H
|  | C | 3 | L
| Project Management | Telegram Chatbot | 4 | H
ZIHAO JING | Technical Skills | Simulink | 3 | H
|  | Matlab | 2 | H
|  | Cadence | 4 | H
| Programming Skills | C | 2 | L
|  | python | 2 | M
KAI NIU | Technical Skills | simulink | 2 | L
|  | matlab | 2 | L
|  | solidworks | 3.5 | M
|  | ubuntu-ros | 4 | H
| Programming Skills | python | 3.5 | M
|  | C | 3 | M
Mena Youssef Gouda | Programming Skills | python
C#
Node JS
Embedded Programming
| DBMS | SQL Server, PostgreSQL
Mongo DB
| Management Skills | Agile
| Technical Skills | IIoT, DAQ, SaaS,PaaS