## TAR for Weeks 2&3
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: Semester 1 | Week | 2&3
|  | Name | Student # | Role
| Team Member 1 | Yunhao Huang | 3132056H | PM/Model-Developer
| Team Member 2 | Xuanwei Ge | 3129788G | Model-Developer
| Team Member 3 | Ramis, Mena Youssef Gouda | 3172685R | Algorithm-Developer
| Team Member 4 | Niu Kai | 3132433N | Algorithm-Developer
| Team Member 5 | Zihao Jing | 3122376J | Model-Developer
| Team Member 6 | Lingyu Guo | 3119118G | Algorithm-Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Project Planning and Requirements Analysis | A1.1 Analyze RoboCup 4v4 competition rules and requirements | 2025-09-29 | 2025-10-05 | 3 | 3 | 3 | 3 | 3 | 3 | 18
2 | Project Planning and Requirements Analysis | A1.2 Define the system architecture | 2025-09-29 | 2025-10-05 | 1 | 0 | 4 | 0 | 0 | 0 | 5
3 | Weekly Meeting | Supervisor meeting | 2025-09-29 | 2025-10-05 | 1 | 1 | 1 | 1 | 1 | 1 | 6
4 | Weekly Meeting | Online meeting | 2025-09-29 | 2025-10-05 | 1 | 1 | 1 | 1 | 1 | 1 | 6
5 | Project Planning and Requirements Analysis | A1.3 Assign team roles and responsibilities | 2025-10-06 | 2025-10-12 | 4 | 2 | 2 | 2 | 2 | 2 | 14
6 | Project Planning and Requirements Analysis | A1.4 Develop project timeline and milestones | 2025-10-06 | 2025-10-12 | 2 | 2 | 2 | 2 | 2 | 2 | 12
7 | Simulation Environment Setup | A2.1 Configure and customize Webots world file | 2025-10-06 | 2025-10-12 | 3 | 3 | 1 | 4 | 3 | 4 | 18
8 | Simulation Environment Setup | A2.2 Import and place four robot models | 2025-10-06 | 2025-10-12 | 2 | 3 | 2 | 0 | 0 | 0 | 7
9 | Simulation Environment Setup | A2.3 Add ball, goals, and initial positioning | 2025-10-06 | 2025-10-12 | 1 | 3 | 0 | 4 | 2 | 1 | 11
10 | Simulation Environment Setup | A2.4 Test simulation stability and environment parameters | 2025-10-06 | 2025-10-12 | 0 | 0 | 2 | 1 | 4 | 4 | 11
11 | Weekly Meeting | Supervisor meeting | 2025-10-06 | 2025-10-12 | 1 | 1 | 1 | 1 | 1 | 1 | 6
12 | Weekly Meeting | Online meeting | 2025-10-06 | 2025-10-12 | 1 | 1 | 1 | 1 | 1 | 1 | 6
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
|  | OVERALL TOTAL |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 120
|  | E- SIGNATURE |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## TAR for Weeks 4&5
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: Semester 1 | Week | 4&5
|  | Name | Student # | Role
| Team Member 1 | Yunhao Huang | 3132056H | PM/Model-Developer
| Team Member 2 | Xuanwei Ge | 3129788G | Model-Developer
| Team Member 3 | Ramis, Mena Youssef Gouda | 3172685R | Algorithm-Developer
| Team Member 4 | Niu Kai | 3132433N | Algorithm-Developer
| Team Member 5 | Zihao Jing | 3122376J | Model-Developer
| Team Member 6 | Lingyu Guo | 3119118G | Algorithm-Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Robot Motion Control (Single Agent) | A3.1 Create basic walking .motion files | 2025-10-13 | 2025-10-19 | 4 | 4 | 2 | 2 | 2 | 1 | 15
2 | Robot Motion Control (Single Agent) | A3.2 Implement walk_forward() and turning control functions | 2025-10-13 | 2025-10-19 | 2 | 2 | 2 | 0 | 3 | 1 | 10
3 | Robot Motion Control (Single Agent) | A3.3 Develop and test kicking motion sequence | 2025-10-13 | 2025-10-19 | 3 | 4 | 0 | 0 | 0 | 3 | 10
4 | Robot Motion Control (Single Agent) | A3.4 Integrate all motion states into a control module | 2025-10-13 | 2025-10-19 | 1 | 1 | 2 | 2 | 3 | 1 | 10
5 | Weekly Meeting | Supervisor meeting | 2025-10-13 | 2025-10-19 | 1 | 1 | 1 | 1 | 1 | 2 | 7
6 | Weekly Meeting | Online meeting | 2025-10-13 | 2025-10-19 | 1 | 1 | 3 | 1 | 1 | 2 | 9
7 | Perception System (Vision and Localization) | A4.1 Capture and process camera images from robot sensors | 2025-10-20 | 2025-10-26 | 0 | 0 | 3 | 5 | 0 | 1 | 9
8 | Perception System (Vision and Localization) | A4.2 Detect ball and goals using color segmentation or OpenCV | 2025-10-20 | 2025-10-26 | 1 | 2 | 1 | 2 | 2 | 2 | 10
9 | Perception System (Vision and Localization) | A4.3 Compute relative positions and orientation for localization | 2025-10-20 | 2025-10-26 | 2 | 1 | 0 | 0 | 1 | 0 | 4
10 | Perception System (Vision and Localization) | A4.4 Visualize perception outputs for debugging | 2025-10-20 | 2025-10-26 | 3 | 2 | 2 | 5 | 5 | 5 | 22
11 | Weekly Meeting | Supervisor meeting | 2025-10-20 | 2025-10-26 | 1 | 1 | 1 | 1 | 1 | 1 | 6
12 | Weekly Meeting | Online meeting | 2025-10-20 | 2025-10-26 | 1 | 1 | 3 | 1 | 1 | 1 | 8
13
14
15
16
17
18
|  | OVERALL TOTAL |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 120
|  | E- SIGNATURE |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## TAR for Weeks 6&7
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: Semester 1 | Week | 6&7
|  | Name | Student # | Role
| Team Member 1 | Yunhao Huang | 3132056H | PM/Model-Developer
| Team Member 2 | Xuanwei Ge | 3129788G | Model-Developer
| Team Member 3 | Ramis, Mena Youssef Gouda | 3172685R | Algorithm-Developer
| Team Member 4 | Niu Kai | 3132433N | Algorithm-Developer
| Team Member 5 | Zihao Jing | 3122376J | Model-Developer
| Team Member 6 | Lingyu Guo | 3119118G | Algorithm-Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Robot Motion Control (Single Agent) | A3.3 Develop and test kicking motion sequence | 2025-10-27 | 2025-11-02 | 6 | 8 | 4 | 2 | 8 | 7 | 35
2 | Robot Motion Control (Single Agent) | A3.4 Integrate all motion states into a control module | 2025-10-27 | 2025-11-02 | 7 | 6 | 4 | 4 | 6 | 1 | 28
3 | Perception System (Vision and Localization) | A4.3 Compute relative positions and orientation for localization | 2025-10-27 | 2025-11-02 | 4 | 5 | 6 | 7 | 5 | 9 | 36
4 | Perception System (Vision and Localization) | A4.4 Visualize perception outputs for debugging | 2025-10-27 | 2025-11-02 | 2 | 3 | 3 | 6 | 5 | 2 | 21
5 | Weekly Meeting | Supervisor meeting | 2025-10-27 | 2025-11-02 | 2 | 2 | 2 | 2 | 2 | 2 | 12
6 | Weekly Meeting | Online meeting | 2025-11-03 | 2025-11-09 | 2 | 2 | 2 | 2 | 2 | 2 | 12
7 | Decision Making and Behavior Control | A5.1 Design state machine (SEARCH → APPROACH → KICK) | 2025-11-03 | 2025-11-09 | 4 | 3 | 3 | 3 | 1 | 2 | 16
8 | Decision Making and Behavior Control | A5.2 Implement behavior transitions and logic thresholds | 2025-11-03 | 2025-11-09 | 3 | 3 | 6 | 5 | 2 | 4 | 23
9 | Weekly Meeting | Supervisor meeting | 2025-11-03 | 2025-11-09 | 2 | 2 | 2 | 2 | 2 | 2 | 12
10 | Weekly Meeting | Online meeting | 2025-11-03 | 2025-11-09 | 2 | 2 | 2 | 2 | 2 | 2 | 12
11 | Extra simspark test | A9.1 The testing of transferring the project to the Simspark software | 2025-11-03 | 2025-11-09 | 6 | 4 | 6 | 5 | 5 | 7 | 33
12
13
14
15
16
17
18
|  | OVERALL TOTAL |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 240
|  | E- SIGNATURE |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## TAR for Weeks 8&9
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: Semester 1 | Week | 8&9
|  | Name | Student # | Role
| Team Member 1 | Yunhao Huang | 3132056H | PM/Model-Developer
| Team Member 2 | Xuanwei Ge | 3129788G | Model-Developer
| Team Member 3 | Ramis, Mena Youssef Gouda | 3172685R | Algorithm-Developer
| Team Member 4 | Niu Kai | 3132433N | Algorithm-Developer
| Team Member 5 | Zihao Jing | 3122376J | Model-Developer
| Team Member 6 | Lingyu Guo | 3119118G | Algorithm-Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Decision Making and Behavior Control | A5.1 Design state machine (SEARCH → APPROACH → KICK) | 2025-11-10 | 2025-11-16 | 8 | 8 | 4 | 4 | 4 | 4 | 32
2 | Decision Making and Behavior Control | A5.2 Implement behavior transitions and logic thresholds | 2025-11-10 | 2025-11-16 | 4 | 6 | 6 | 4 | 6 | 2 | 28
3 | Decision Making and Behavior Control | A5.3 Tune decision parameters (distance, angle thresholds) | 2025-11-10 | 2025-11-16 | 6 | 8 | 0 | 0 | 4 | 4 | 22
4 | Decision Making and Behavior Control | A5.4 Integrate perception and motion into a unified controller | 2025-11-10 | 2025-11-16 | 2 | 2 | 6 | 6 | 8 | 4 | 28
5 | Weekly Meeting | Supervisor meeting | 2025-11-10 | 2025-11-16 | 2 | 2 | 2 | 2 | 2 | 2 | 12
6 | Weekly Meeting | Online meeting | 2025-11-17 | 2025-11-23 | 2 | 2 | 4 | 2 | 2 | 2 | 14
7 | Multi-Robot Cooperation and Communication | A6.1 Establish inter-robot communication (UDP/TCP or Supervisor control) | 2025-11-17 | 2025-11-23 | 6 | 4 | 6 | 6 | 2 | 4 | 28
8 | Multi-Robot Cooperation and Communication | A6.2 Implement role assignment (Goalkeeper, Forward, Defender, Support) | 2025-11-17 | 2025-11-23 | 6 | 4 | 2 | 4 | 4 | 4 | 24
9 | Weekly Meeting | Supervisor meeting | 2025-11-17 | 2025-11-23 | 2 | 2 | 2 | 2 | 2 | 2 | 12
10 | Weekly Meeting | Online meeting | 2025-11-17 | 2025-11-23 | 2 | 2 | 2 | 2 | 2 | 2 | 12
11 | Multi-Robot Cooperation and Communication | A7.1 Define test scenarios (ball control, passing, defense) | 2025-11-17 | 2025-11-23 | 0 | 0 | 6 | 8 | 4 | 10 | 28
12
13
14
15
16
17
18
|  | OVERALL TOTAL |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 240
|  | E- SIGNATURE |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## TAR for Weeks 1&2
Fortnightly Time Allocation Record
| Team Number: 8 | Reporting Period: Semester 2 | Week | 1&2
|  | Name | Student # | Role
| Team Member 1 | Yunhao Huang | 3132056H | PM/Model-Developer
| Team Member 2 | Xuanwei Ge | 3129788G | Model-Developer
| Team Member 3 | Ramis, Mena Youssef Gouda | 3172685R | Algorithm-Developer
| Team Member 4 | Niu Kai | 3132433N | Algorithm-Developer
| Team Member 5 | Zihao Jing | 3122376J | Model-Developer
| Team Member 6 | Lingyu Guo | 3119118G | Algorithm-Developer
# | Workpackage | Activity | Start Date | End Date | Hours: Team member 1 | Hours: Team member 2 | Hours: Team member 3 | Hours: Team member 4 | Hours: Team member 5 | Hours: Team member 6 | Total hours
1 | Pitch Presentation | A10.1 Define pitch storyline and key messages | 2026-01-15 | 2026-01-25 | 5 | 4 | 6 | 5 | 6 | 4 | 30
2 | Pitch Presentation | A10.2 Create pitch slide deck | 2026-01-15 | 2026-01-25 | 4 | 6 | 5 | 5 | 6 | 2 | 28
3 | Pitch Presentation | A10.3 Prepare key visuals/diagrams | 2026-01-15 | 2026-01-25 | 5 | 4 | 3 | 3 | 7 | 6 | 28
4 | Pitch Presentation | A10.4 Produce pitch demo video | 2026-01-15 | 2026-01-25 | 2 | 5 | 2 | 6 | 4 | 6 | 25
5 | Weekly Meeting | Supervisor meeting | 2026-01-15 | 2026-01-25 | 2 | 2 | 2 | 2 | 2 | 2 | 12
6 | Weekly Meeting | Online meeting | 2026-01-15 | 2026-01-25 | 2 | 2 | 4 | 2 | 2 | 2 | 14
7 | Pitch Presentation | A10.5 Integrate supporting materials (results/metrics + repo snapshot + run steps) | 2026-01-26 | 2026-02-01 | 8 | 7 | 6 | 6 | 2 | 7 | 36
8 | Pitch Presentation | A10.6 Rehearsal and Q&A preparation (timed run + backup plan) | 2026-01-26 | 2026-02-01 | 8 | 6 | 8 | 7 | 7 | 7 | 43
9 | Weekly Meeting | Supervisor meeting | 2026-01-26 | 2026-02-01 | 2 | 2 | 2 | 2 | 2 | 2 | 12
10 | Weekly Meeting | Online meeting | 2026-01-26 | 2026-02-01 | 2 | 2 | 2 | 2 | 2 | 2 | 12
11
12
13
14
15
16
17
18
|  | OVERALL TOTAL |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 240
|  | E- SIGNATURE |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!